## Slide 1
Evaluability Assessment critical for successful Evaluations
By Sylvester Kato Technical M&E in the BMAU UEA Conference, February 2019 Kampala Uganda
Annual Evaluation conference February 11th to 15th 2019

## Slide 2: Evaluability Assessment

## Slide 3: Presentation outline
  Introduction to EA
  Where is Evaluability lost
  Key steps in evaluability Assessment
  Key EA Questions
  Crucial Steps
  Conclusion

## Slide 4: Evaluability Assessment
  Evaluability assessment is ‘‘a pre-evaluation appraisal of whether a program’s performance can be evaluated and if so whether it should be’’ (Rossi, Freeman, & Lipsey 1999).
  Systematic process to determine whether program evaluation is feasible.
  Decide whether an evaluation is useful to provide timely, relevant findings for decision makers.
  Evaluation research will be pointless if the program itself cannot be evaluated.
  Yes, some type of study is always possible, but a study specifically to identify the effects of a particular program may not be possible within the available time and resources.
  So researchers may conduct an evaluability assessment to learn this in advance, rather than expend time and effort on a fruitless project.

## Slide 5: Evaluability Assessment
  Assesses:
  Underlying program logic
  Current state of program implementation
  Feasibility of conducting rigorous outcomes-focused evaluation or other sorts of evaluation

## Slide 6: Evaluability Assessment

## Slide 7: Loss of Evaluability
Review of Dutch Private Sector Programs
 2/3 of executed ‘evaluations’ cannot be used
Major reasons:
- Evaluation agency not fully independent
- stated objectives too broad/vague
- no clear indicators defined
- data at too aggregate level
- absence of baseline data
- no representative sampling
- too general intervention theory

## Slide 8: Key steps in evaluability Assessment
Smith (1989): ten steps procedure for Evaluability Assessment
 initial diagnostics
  Identify relevant stakeholders
  Define boundaries of the program
  Analyze available program documents
  Clarify intervention theory (goals, resources, activities, outcomes)

## Slide 9: Key steps in evaluability Assessment
  Analyze stakeholders perceptions of the program
  Assess target population(s)
  Discuss differences in outcome perceptions
  Determine plausibility of intervention model
  Discuss validity of the program
  Decide about continuation (= full evaluation)

## Slide 10: Key EA Questions
Does the program serve the population for whom it was designed?
Does the program have the resources (available/used) as scheduled in the program design?
Are the program activities being implemented as designed?
4. Does the program have the capacity to provide data for
an evaluation?

## Slide 11: Crucial Steps
EA has five crucial tasks that an evaluator must successfully complete:
• Task 1. Study the program history, design, and operation;
• Task 2. Watch the program in action (participants)
• Task 3. Determine the program’s capacity for data collection,
management and analysis;
• Task 4. Assess the likelihood that the program will reach its
goals and objectives (consistency)
• Task 5. Show whether an evaluation is feasibly (will help the program and its stakeholders).

## Slide 12: Conclusion
The overall purpose of an Evaluability Assessment is to inform the timing of an evaluation and to improve the prospects for an evaluation producing useful results.
Evaluability assessments can be configured to cast new light on developments in the field families or clusters of policies and programs.
Although the most common focus of an Evaluability Assessment is a single project, Evaluability Assessments should also been carried out on sets of projects, policy areas, country strategies, strategic plans, work plans, and partnerships to increase chances of utilization